## Candidates
Candidate | Category | Mandatory | Requires | Option | Value | 2027 | 2028 | 2029 | 2030 | 2031
Fleet sustainment | Readiness | yes |  | Full | 30 | 420 | 430 | 440 | 450 | 460
Munitions buy | Readiness |  |  | Full rate | 25 | 180 | 180 | 180 | 180 | 180
Munitions buy |  |  |  | Minimum sustaining rate | 14 | 90 | 90 | 90 | 90 | 90
Sensor: upgrade in place | Modernization |  |  | Fund | 18 | 120 | 160 | 140 | 60 | 60
Sensor: new development | Modernization |  |  | Start now | 34 | 150 | 260 | 300 | 280 | 200
Sensor: new development |  |  |  | Defer two years | 24 |  |  | 150 | 260 | 300
Long-range missile | Modernization |  |  | Full | 28 | 140 | 180 | 200 | 200 | 200
Missile integration | Modernization |  | Long-range missile | Full | 9 |  | 30 | 40 | 40 | 40
Training ranges | Infrastructure |  |  | Full | 7 | 40 | 40 | 40 | 40 | 40
Cyber hardening | Infrastructure |  |  | Full | 11 | 60 | 60 | 60 | 60 | 60

## Budget
Year | Budget
2027 | 1000
2028 | 1050
2029 | 1100
2030 | 1100
2031 | 1100

## Exclusive
Candidates
Sensor: upgrade in place; Sensor: new development

## Settings
Setting | Value
Units | TY $M
Delta | 50
Growth Low | 0.92
Growth Most Likely | 1
Growth High | 1.45
Growth Correlation | 0.3
Seed | 7
Description | Invented programs and numbers, for illustration only. Then-year $M, a five-year plan.

## Instructions
Sheet or topic | What to put there
What this is | Candidate programs, their funding options and the budget, for choosing what to fund: ce-core portfolio --spec <this file>.
Candidates sheet | One row per funding option. A candidate with several options (full rate, minimum rate, defer) takes one row each; at most one is funded. Value is the benefit score. The year columns hold the cost in each year. Category, Mandatory (yes to always fund it) and Requires (candidates it depends on, separated by ;) go on its first row.
Budget sheet | The money available in each year.
Exclusive sheet | Candidates only one of which may be funded, separated by ; on a row.
Settings sheet | Growth Low, Most Likely and High are the cost growth factors for the risk analysis (0.92, 1.0, 1.45). Delta is the budget step for the trade-off curve.