## Elements
Element | Point Estimate | Low | Most Likely | High | Distribution
1.0 Program management | 12 | 11 | 12 | 18 | triangular
2.0 Systems engineering | 18.5 | 17 | 18.5 | 28 | triangular
3.0 Antenna subsystem | 42 | 37 | 42 | 72 | triangular
4.0 Software | 36 | 31 | 36 | 90 | triangular
5.0 Facilities | 22 | 20 | 22 | 31 | pert
6.0 Integration and test | 15 | 13 | 15 | 30 | triangular
7.0 Training and support | 6.5 | 6 | 6.5 | 10 | pert
8.0 Initial spares | 4
Note on A1: Required. The WBS element's name, e.g. 1.0 Air vehicle. Each name once.
Note on B1: Required. The number in your estimate for this element, in the units on the Settings sheet.
Note on C1: Optional. The least it could plausibly cost. Leave Low and High blank for an element with no uncertainty.
Note on D1: Optional. The single most likely cost; blank means the point estimate.
Note on E1: Optional. The most it could plausibly cost.
Note on F1: Optional. The shape between Low and High: triangular (the default), pert, uniform, or lognormal (Low and High are then the ends of an 80% range, as a CER gives).

## Risks
Risk | Probability | Low | Most Likely | High | Element
Antenna vendor requalification | 25% | 4 | 6 | 10 | 3.0 Antenna subsystem
Cyber accreditation rework | 40% | 2 | 3 | 6 | 4.0 Software
Site permitting delay | 15% | 1.5 | 3 | 5 | 5.0 Facilities
Note on A1: Required. What might happen, e.g. Qualification test failure.
Note on B1: Required. The chance it happens: 0.3 or 30%.
Note on C1: Optional. The least it would cost if it happens.
Note on D1: Required. The most likely cost if it happens.
Note on E1: Optional. The most it would cost if it happens.
Note on F1: Optional. Optional: the element it belongs to, for the report. Must match a name on the Elements sheet.

## Correlation
Element A | Element B | Correlation
4.0 Software | 6.0 Integration and test | 0.6
1.0 Program management | 2.0 Systems engineering | 0.5
2.0 Systems engineering | 4.0 Software | 0.4
Note on A1: Required. One element of a pair that tends to overrun together.
Note on B1: Required. The other element of the pair.
Note on C1: Required. How strongly they move together, -1 to 1 (0.3 is a common default; pairs not listed take the Settings value).

## Settings
Setting | Value
Units | millions
Default Correlation | 0.3
Iterations | 20000
Seed | 1
Note on A2: What the costs are in: dollars, thousands, millions, billions or any word.
Note on A3: How much elements not paired on the Correlation sheet move together (0.3 is usual).
Note on A4: How many simulations: 20,000 is plenty.
Note on A5: Any whole number; the same seed gives the same answer.

## Instructions
How to fill in this workbook
Yellow cells | Yours to fill in. The example rows are there to show the layout: type over them, and add more rows in the yellow space below.
Dark blue heading | A column that must be filled in.
Light blue heading | An optional column: leave it blank if it doesn't apply.
Grey cells | Labels: leave them as they are.
Hover over a heading | A note says what goes in that column, in what units, with an example. A small arrow in a cell means a drop-down list of the allowed answers.
Sheet or topic | What to put there
What this is | A cost estimate with its uncertainty. ce-core cost-risk --data <this file> simulates it and says how much it takes to be 50%, 80% or 90% sure, which elements and risks drive that, and what the correlation between elements adds.
Elements sheet | One row per WBS element. Element is its name. Point Estimate is the number in the estimate. Low, Most Likely and High are the range you believe: Low the least it could plausibly cost, High the most. Leave Low and High blank for an element with no uncertainty (it is carried at its point estimate).
Distribution | Optional. triangular (the default) spreads the chance evenly along the three points; pert bunches it toward the most likely; uniform treats every value between Low and High alike and ignores the most likely. lognormal takes Low and High as the ends of an 80% range (Lognormal Range on the Settings sheet changes it) and ignores the most likely: the usual shape for an estimate from a CER, and ce-core cer writes the rows to copy here.
Risks sheet | Things that may or may not happen. Probability is the chance it does (0.3 or 30%). Low, Most Likely and High are what it costs if it does. Element is optional and only labels the report. Delete the rows if there are no risks.
Correlation sheet | Pairs of elements that tend to overrun together, and how strongly (0 none, 1 in lockstep; 0.2 to 0.3 is typical, 0.5 or more for elements driven by the same thing). Every pair not listed takes the Default Correlation on the Settings sheet. Leaving correlation out makes the P80 too low.
Settings sheet | Units labels the money (thousands, millions or any word). Default Correlation applies to every pair not listed. Iterations and Seed control the simulation; the same seed gives the same answer.
Money | Use one unit and one dollar basis (for example constant FY2026 $M) throughout.