## Data
Period | Control Account | Planned Value (BCWS) | Earned Value (BCWP) | Actual Cost (ACWP) | Contractor EAC
2025-10 | 1.1 Air vehicle | 18.9 | 14.5 | 16.2 | 9000
2025-11 | 1.1 Air vehicle | 54.9 | 24.8 | 25.5 | 9030.8
2025-12 | 1.1 Air vehicle | 97 | 51.5 | 56.7 | 9061.5
2026-01 | 1.1 Air vehicle | 142.5 | 77.3 | 84.7 | 9092.3
2026-02 | 1.1 Air vehicle | 189.6 | 112.5 | 127.5 | 9123.1
2026-03 | 1.1 Air vehicle | 236.8 | 161.8 | 177.2 | 9153.8
2026-04 | 1.1 Air vehicle | 283 | 192.8 | 216.4 | 9184.6
2026-05 | 1.1 Air vehicle | 326.9 | 230.6 | 272 | 9215.4
2026-06 | 1.1 Air vehicle | 367.6 | 246.4 | 274.5 | 9246.2
2026-07 | 1.1 Air vehicle | 404.2 | 275.3 | 342.2 | 9276.9
2026-08 | 1.1 Air vehicle | 435.9 | 290.8 | 329.5 | 9307.7
2026-09 | 1.1 Air vehicle | 462.1 | 319.3 | 366.1 | 9338.5
2026-10 | 1.1 Air vehicle | 482.2 | 383.4 | 388.1 | 9369.2
2026-11 | 1.1 Air vehicle | 495.8 | 359.5 | 353.6 | 9400
2026-12 | 1.1 Air vehicle | 502.7
2027-01 | 1.1 Air vehicle | 502.7
2027-02 | 1.1 Air vehicle | 495.8
2027-03 | 1.1 Air vehicle | 482.2
2027-04 | 1.1 Air vehicle | 462.1
2027-05 | 1.1 Air vehicle | 435.9
2027-06 | 1.1 Air vehicle | 404.2
2027-07 | 1.1 Air vehicle | 367.6
2027-08 | 1.1 Air vehicle | 326.9
2027-09 | 1.1 Air vehicle | 283
2027-10 | 1.1 Air vehicle | 236.8
2027-11 | 1.1 Air vehicle | 189.6
2027-12 | 1.1 Air vehicle | 142.5
2028-01 | 1.1 Air vehicle | 97
2028-02 | 1.1 Air vehicle | 54.9
2028-03 | 1.1 Air vehicle | 18.9
2025-10 | 1.2 Software | 8.4 | 5.5 | 6.8 | 4000
2025-11 | 1.2 Software | 24.4 | 9.1 | 10.3 | 4026.9
2025-12 | 1.2 Software | 43.1 | 19.4 | 21.5 | 4053.8
2026-01 | 1.2 Software | 63.3 | 29.6 | 33.3 | 4080.8
2026-02 | 1.2 Software | 84.3 | 37.3 | 45.6 | 4107.7
2026-03 | 1.2 Software | 105.3 | 53.2 | 62 | 4134.6
2026-04 | 1.2 Software | 125.8 | 67.6 | 85.1 | 4161.5
2026-05 | 1.2 Software | 145.3 | 73.9 | 84.3 | 4188.5
2026-06 | 1.2 Software | 163.4 | 94.6 | 107.7 | 4215.4
2026-07 | 1.2 Software | 179.6 | 137.4 | 173 | 4242.3
2026-08 | 1.2 Software | 193.7 | 180.1 | 185.2 | 4269.2
2026-09 | 1.2 Software | 205.4 | 198.1 | 212.5 | 4296.2
2026-10 | 1.2 Software | 214.3 | 169.4 | 183.8 | 4323.1
2026-11 | 1.2 Software | 220.4 | 158.5 | 184.4 | 4350
2026-12 | 1.2 Software | 223.4
2027-01 | 1.2 Software | 223.4
2027-02 | 1.2 Software | 220.4
2027-03 | 1.2 Software | 214.3
2027-04 | 1.2 Software | 205.4
2027-05 | 1.2 Software | 193.7
2027-06 | 1.2 Software | 179.6
2027-07 | 1.2 Software | 163.4
2027-08 | 1.2 Software | 145.3
2027-09 | 1.2 Software | 125.8
2027-10 | 1.2 Software | 105.3
2027-11 | 1.2 Software | 84.3
2027-12 | 1.2 Software | 63.3
2028-01 | 1.2 Software | 43.1
2028-02 | 1.2 Software | 24.4
2028-03 | 1.2 Software | 8.4
2025-10 | 1.3 Systems engineering | 5.2 | 4.9 | 5 | 2500
2025-11 | 1.3 Systems engineering | 15.2 | 16.9 | 18.3 | 2503.8
2025-12 | 1.3 Systems engineering | 27 | 24.7 | 28.4 | 2507.7
2026-01 | 1.3 Systems engineering | 39.6 | 32.1 | 39.3 | 2511.5
2026-02 | 1.3 Systems engineering | 52.7 | 38.3 | 39.6 | 2515.4
2026-03 | 1.3 Systems engineering | 65.8 | 46.9 | 48.1 | 2519.2
2026-04 | 1.3 Systems engineering | 78.6 | 49.3 | 50.6 | 2523.1
2026-05 | 1.3 Systems engineering | 90.8 | 49.5 | 54.1 | 2526.9
2026-06 | 1.3 Systems engineering | 102.1 | 95.2 | 106.5 | 2530.8
2026-07 | 1.3 Systems engineering | 112.3 | 117.3 | 123.2 | 2534.6
2026-08 | 1.3 Systems engineering | 121.1 | 118 | 130 | 2538.5
2026-09 | 1.3 Systems engineering | 128.4 | 143.5 | 156.5 | 2542.3
2026-10 | 1.3 Systems engineering | 133.9 | 165 | 186.2 | 2546.2
2026-11 | 1.3 Systems engineering | 137.7 | 152.9 | 161.1 | 2550
2026-12 | 1.3 Systems engineering | 139.6
2027-01 | 1.3 Systems engineering | 139.6
2027-02 | 1.3 Systems engineering | 137.7
2027-03 | 1.3 Systems engineering | 133.9
2027-04 | 1.3 Systems engineering | 128.4
2027-05 | 1.3 Systems engineering | 121.1
2027-06 | 1.3 Systems engineering | 112.3
2027-07 | 1.3 Systems engineering | 102.1
2027-08 | 1.3 Systems engineering | 90.8
2027-09 | 1.3 Systems engineering | 78.6
2027-10 | 1.3 Systems engineering | 65.8
2027-11 | 1.3 Systems engineering | 52.7
2027-12 | 1.3 Systems engineering | 39.6
2028-01 | 1.3 Systems engineering | 27
2028-02 | 1.3 Systems engineering | 15.2
2028-03 | 1.3 Systems engineering | 5.2
Note on A1: Required. The month the row reports: 2026-01, 1/31/2026 or 1, 2, 3.
Note on B1: Optional. Optional label; with it every account is analysed as well as the total.
Note on C1: Required. Budgeted cost of work scheduled in the period (not cumulative).
Note on D1: Required. Budgeted cost of work performed in the period.
Note on E1: Required. Actual cost of work performed in the period.
Note on F1: Optional. Optional: the contractor's estimate at completion as reported.

## Instructions
How to fill in this workbook
Yellow cells | Yours to fill in. The example rows are there to show the layout: type over them, and add more rows in the yellow space below.
Dark blue heading | A column that must be filled in.
Light blue heading | An optional column: leave it blank if it doesn't apply.
Grey cells | Labels: leave them as they are.
Hover over a heading | A note says what goes in that column, in what units, with an example. A small arrow in a cell means a drop-down list of the allowed answers.
Column or topic | What to put there
What this workbook is | The input for `ce-core evm --data my_evm.xlsx`. The Data sheet holds an invented example program so the layout is plain: replace it with yours.
One row per | Reporting period, per control account. Without a Control Account column, one row per period for the whole program.
Period | The month the row reports: 2026-01, 1/31/2026 or a number 1, 2, 3 ... all work. Periods sort by date.
Control Account | Optional. Any label. With it, every account is analysed as well as the program total.
Planned Value (BCWS) | What the baseline planned to be done in that period. Fill it in for every period to the end of the plan, including the future.
Earned Value (BCWP) | The budgeted value of the work actually done in that period. Leave blank after the latest (status) period.
Actual Cost (ACWP) | What that work actually cost in that period. Leave blank after the status period.
Contractor EAC | Optional. The contractor's estimate at completion, if reported.
Per period, not to date | Each value is that period's own amount. For cumulative to-date values instead, run with --cumulative.
Units | Any one currency unit throughout: dollars, thousands or millions. Say which with --units thousands (or dollars, millions) for the labels; nothing is converted.
Other column names | PV, EV, AC, 'Planned Value', 'Month', 'WBS' and similar are recognised too, so an export from another tool may read as it is.
From an IPMDAR | No need for this workbook: `ce-core evm --ipmdar the_delivery.zip`.