## Activities
ID | Name | Duration | Duration Low | Duration Most Likely | Duration High | Duration Distribution | Predecessors | Fixed Cost | Cost Low | Cost Most Likely | Cost High | Cost Distribution | Burn Rate
design | Design through CDR | 12 | 10.8 | 12 | 16.8 | [7 empty] | 1.5
bus | Spacecraft bus build | 18 | 16.2 | 18 | 25.2 |  | design | 40 | 38 | 40 | 52 |  | 1
instrument | Instrument development | 20 | 18 | 20 | 34 |  | design | 30 | 28.5 | 30 | 45 |  | 1.2
fsw | Flight software | 16 | 14.4 | 16 | 25.6 |  | design -4 | [5 empty] | 0.8
i&t | Integration and test | 8 | 7.2 | 8 | 14.4 |  | bus; instrument; fsw | [5 empty] | 2.5
launch | Launch campaign | 3 |  |  |  |  | i&t | 12 |  |  |  |  | 1
Note on A1: Required. A short name other rows refer to, e.g. design.
Note on B1: Optional. A longer description.
Note on C1: Required. Months, most likely.
Note on D1: Optional. Shortest plausible duration, months.
Note on E1: Optional. Most likely duration, months.
Note on F1: Optional. Longest plausible duration, months.
Note on G1: Optional. triangular (default), pert or uniform.
Note on H1: Optional. IDs it waits for, separated by ;, each optionally with a link type and lag: design; fsw -4; bus SS +2.
Note on I1: Optional. Cost spent whatever the duration.
Note on J1: Optional. Lowest plausible fixed cost.
Note on K1: Optional. Most likely fixed cost.
Note on L1: Optional. Highest plausible fixed cost.
Note on M1: Optional. triangular (default), pert or uniform.
Note on N1: Optional. Cost per month the activity runs.

## Risks
Risk | Probability | Activities | Delay Low | Delay Most Likely | Delay High | Delay Distribution | Cost
Detector yield below plan | 0.3 | instrument | 2 | 3 | 6 |  | 6
Thermal vacuum retest | 0.2 | i&t |  | 2 |  |  | 3
Note on A1: Required. What might happen.
Note on B1: Required. The chance it happens: 0.3 or 30%.
Note on C1: Required. The activity IDs it delays, separated by ;.
Note on D1: Optional. Shortest delay if it happens, months.
Note on E1: Optional. Most likely delay, months (or the only delay).
Note on F1: Optional. Longest delay, months.
Note on G1: Optional. triangular (default), pert or uniform.
Note on H1: Optional. Cost it adds besides the delay.

## Settings
Setting | Value
Name | Example science mission
Units | $M
Standing Army | 1.2
Duration Correlation | 0.5
Cost Correlation | 0.3
Confidence | 0.7
Iterations | 20000
Seed | 1
Description | Invented numbers, for illustration only: a small science spacecraft from design to launch, in months and $M.
Note on A2: The project's name, for the report.
Note on A3: What the costs are in.
Note on A4: Cost per month of the whole project running.
Note on A5: How much durations move together, 0 to 1.
Note on A6: How much costs move together, 0 to 1.
Note on A7: The joint confidence to report: 0.7 for 70%.
Note on A8: How many simulations.
Note on A9: Any whole number; the same seed gives the same answer.

## Instructions
How to fill in this workbook
Yellow cells | Yours to fill in. The example rows are there to show the layout: type over them, and add more rows in the yellow space below.
Dark blue heading | A column that must be filled in.
Light blue heading | An optional column: leave it blank if it doesn't apply.
Grey cells | Labels: leave them as they are.
Hover over a heading | A note says what goes in that column, in what units, with an example. A small arrow in a cell means a drop-down list of the allowed answers.
Sheet or topic | What to put there
What this is | A project network with its uncertainty, for a joint cost and schedule (JCL) analysis: ce-core jcl --spec <this file>.
Activities sheet | One row per activity. ID is a short name the other rows refer to. Duration is in months; Duration Low, Most Likely and High are the range you believe (leave them blank for none). Predecessors lists the activities it waits for, separated by ;, each optionally with a link type and a lag in months: design; fsw -4; bus SS +2.
Costs | Fixed Cost is spent whatever the duration, with Cost Low, Most Likely and High as its range. Burn Rate is spent per month the activity runs, so it grows when the activity slips.
Risks sheet | Events that may happen. Probability is the chance (0.3 or 30%), Activities the IDs it delays (separated by ;), Delay the months it adds (one number, or Low, Most Likely and High), Cost what it adds besides the delay.
Settings sheet | Standing Army is the cost per month of the whole project running. The correlations say how much durations, and costs, move together. Confidence is the joint level to report against (0.7 for 70%).
Distribution columns | Optional: triangular (the default), pert or uniform.